# Individual plan

Preliminary title
Design and Evaluation of Real-Time Feedback for Movement Validity in Functional Fitness Training

Student (name & email)
Chi Chen — chich@kth.se

Course code
DA256X

Examiner at KTH
Leif Dahlberg

Supervisor at KTH
Qiaoqiao Ren

Current date / Start date
2026-02-03

Keywords
hiit training; hci; smartphone sensors; pose estimation; fatigue; technique degradation; real-time feedback; audio feedback; haptics

## BACKGROUND & OBJECTIVE

Description of the area within which the degree project is being carried out with connection to scientific and/or societal interest.

As participation in CrossFit and HYROX increases, athletes perform workouts that require strict repetition counting and, in many movements, judgment of movement validity (e.g., whether a repetition meets a predefined standard). In competitions, this role is carried out by judges; in everyday training, athletes often self-count or rely on informal peer feedback, which can be inconsistent and error-prone—especially during high-intensity efforts when attention is limited.

This degree project explores an “electronic judge assistant” that automatically counts repetitions for selected functional fitness movements and provides real-time feedback (audio/vision). The project is scientifically relevant to Human–Computer Interaction (HCI) and mobile sensing / computer vision, because it studies how automated assessment and feedback should be designed for users during intense physical activity. Societally, an accessible e-judge tool could support safer and more standardized training, and reduce reliance on human judges outside competition settings.

Description of the interest of the organization or company who provided the assignment.

No external organization is providing the assignment. The primary stakeholders are the CrossFit and HYROX communities, including athletes and coaches, who can benefit from a low-cost and accessible assistant for repetition counting and movement-standard reminders.

The high level objective of the project, the desired outcome from the perspective of the assignment provider.

The high-level objective is to develop and evaluate a smartphone application that:

- Counts repetitions for 2-3 selected functional fitness movements;

- Provides real-time feedback (audio + vision) that

(a) informs athletes of the current rep count;

(b) alerts them when a repetition is likely not meeting the movement standard;

- Evaluates

(a) counting/validity accuracy and

(b) the user impact of feedback, including satisfaction, helpfulness, and disruption.

The background knowledge required to carry out the project.

- Machine learning / computer vision fundamentals for movement detection (e.g., pose-based features or video-based classification) and evaluation metrics

e.g. Mediapipe, Kinect computing…

- Mobile prototyping and app development (smartphone sensing, real-time inference constraints, UI/UX integration)

- HCI evaluation methods (usability testing, questionnaires, and interview techniques)

- Basic movement standards and common faults in CrossFit/HYROX-relevant movements

## RESEARCH QUESTION & METHOD

QUESTION: State the question that will be examined. Formulate is an explicit and evaluable question. State your hypothesis.

### RQ1 (accuracy / feasibility)

RQ1: How accurate is the smartphone-based tool in (a) repetition counting and (b) detecting likely invalid repetitions for 2-3 selected movements, under realistic training conditions—and is this accuracy sufficient for use as an assisting judge tool?

Hypothesis H1: The system achieves counting accuracy and invalid-rep detection performance that is significantly better than baseline heuristics (e.g., simple timing-based counting), and is reliable enough to support athletes as an assisting judge in training contexts.

### RQ2 (user impact of feedback)

RQ2: How do athletes perceive the real-time feedback in terms of timing, disruption, helpfulness, and trust—and does it meaningfully support self-directed training compared to no feedback?

Hypothesis H2: Audio+haptic feedback increases perceived helpfulness and training confidence, and improves awareness of movement standards, while keeping disruption at an acceptable level.

Objectives: Break down the research questions to measurable objectives.

### Target movements (2-3)

- Air Squat

- Wall Ball

- Deadlift

### Objectives (measurable)

1 Rep counting accuracy
 Develop a tool that counts repetitions for the three movements in real time.

2 “Standard reminder” detection (lightweight validity cues)
 Implement detection for 1–2 key movement-standard indicators per movement and trigger feedback when a likely violation occurs.

3 Feedback design (audio)
 Design and implement real-time audio and visual feedback patterns for (1) rep count updates and (2) standard reminders.

4 Evaluation (accuracy + user impact)
 Evaluate (1) counting/standard-reminder performance and (2) user experience (timing, disruption, helpfulness, trust) with ~10 participants.

Tasks: Describe the tasks that are necessary to reach the objectives. For each task, describe the challenges it involves.

T1  Define standards & annotation scheme

- Define 1–2 measurable cues per movement (below).

- Prepare labeling guidelines and examples for consistent annotation.
Challenges: movement standards can be ambiguous under monocular video; need operational definitions.

T2  Data collection & dataset preparation

- Record sessions with standardized camera setup and lighting guidance.

- Annotate rep boundaries and standard cues.
Challenges: varied body sizes, camera angles.

T3  Baseline implementation

- Baselines such as peak/valley heuristics from pose landmarks and rep-tempo rules.
Challenges: baseline robustness; helps establish meaningful comparison.

T4  ML model for rep segmentation/counting

- Use pose-based time series for rep segmentation and counting.
Challenges: latency and small dataset; need cross-validation and careful feature selection.

T5  Feedback implementation

- Integrate audio + visual feedback.
Challenges: not distracting during HIIT; timing must be appropriate.

T6  User study & analysis

- Within-subject evaluation: no feedback vs feedback, counterbalanced.
Challenges: learning effects and fatigue differences; mitigate with short standardized blocks.

Method: Describe the method/s that will be followed. Explain why they are appropriate for the project or for the specific tasks.

This project follows a smart-phone prototype HCI methodology combined with quantitative system evaluation and user-centered evaluation.

- Iterative prototyping: Build a web-based smartphone prototype using camera input and real-time pose estimation (e.g., MediaPipe Pose). Implement rep counting with pose-based features and simple state-machine logic, then refine through pilot testing.

Why: Rapid iteration on real devices is appropriate for a practical “e-judge” tool.

- Technical evaluation: Measure counting performance against manual ground truth (e.g., rep count error and event precision/recall, plus feedback latency).

Why: Directly answers whether the system is accurate enough to assist counting.

- User evaluation: Run a small within-subject study (~10 participants) comparing audio feedback using questionnaires and short interviews (timing, disruption, helpfulness, satisfaction).

Why: Needed to assess the impact and acceptability of real-time feedback during HIIT training.

Ethics and Sustainability: Does the project address questions of ethics or sustainability? Does the project raise ethical or sustainability questions? If yes, how could these be handled?

Yes, the project raises ethical questions mainly related to privacy, consent, and safe use.

Video and personal data privacy: The prototype uses a phone camera and may record or process video where participants can be identifiable.
Handling: obtain informed consent; clearly explain what is collected (video vs pose landmarks vs logs); minimize data collection; store data securely with access control; allow participants to withdraw their data.

Limitations: Define the limitations on what is to be done (so that it is clear what is not included in the degree project).

Assistive tool, not official judging: The system is designed as an electronic judge assistant for training support. It is not intended to replace official competition judges, and it does not guarantee rulebook-level validity decisions in all cases.

Limited movement scope: The prototype covers only three movements: air squat, wall ball, and deadlift. Other CrossFit/HYROX movements are out of scope.

Small-scale evaluation: The user study targets ~10 participants, focusing on feasibility, usability, and initial performance evidence. Results will not claim broad generalization to all athletes, environments, or camera setups.

No long-term behavior outcomes: The project evaluates short-term usability and immediate perceived impact; it does not measure long-term training improvement or injury reduction.

Risks: Explain what can go wrong and delay or make the project impossible to conclude. Explain how you will deal with these problems.

- Browser/device issues (camera/audio/performance): may not run reliably on some phones.
Mitigation: test early on iOS/Android; recommend supported browsers; keep processing lightweight.

- Pose errors from angle/lighting/occlusion: can reduce counting accuracy.
Mitigation: standardize camera setup with a simple guide; report results only for tested conditions.

- Unstable rep logic across users: thresholds may not generalize.
Mitigation: normalize features; run an early pilot (2–3 users) to tune; keep a simple baseline fallback.

EVALUATION & NEWS VALUE

Evaluation: How is it determined if the objectives of the degree project have been fulfilled and if the research question has been adequately answered? What kind of qualitative or quantitative measures can be defined and evaluated?

Expected scientific results: How is the work scientifically relevant?

The work's innovation/news value. Why does someone want to read the finished work? And who are these people?

PRE-STUDY

Description of the literature studies. What areas will the literature study focus on? How shall the necessary knowledge on background and state-of-the-art be obtained? What preliminarily important references have been identified?

CONDITIONS & SCHEDULE

List of the resources are needed to solve the problem. This can be technical equipment, software, or data, but also experiment and interview subjects.

Resources needed

Hardware: Smartphone with camera (participant phones or one test phone), basic phone stand/tripod.

Software/Tools: Web development stack (TypeScript/JavaScript, React/Vite), MediaPipe Pose (web), Git/GitHub, simple data export (JSON/CSV).

Data: Self-collected recordings/logs from prototype sessions (pose landmarks + rep events; optional video if consented).

Participants: ~10 participants for evaluation (plus 2–3 for an early pilot); short questionnaire + brief interview.

Provide a project timeline, specifying the main tasks and the time allocated for them, milestones (time of achievement of intermediate goals)

W1–2: Web prototype skeleton

Milestone: camera works on phone + pose landmarks running

W3–4: Baseline rep counting for 3 movements + audio feedback

Milestone: air squat / wall ball / deadlift counting + beep feedback

W5: Logging + export (JSON/CSV) + simple UI polishing

Milestone: “session → export logs” works reliably

W6: Pilot (2–3 users) + parameter tuning

Milestone: pilot completed + updated thresholds / stability fixes

W7–10: Pre-study / related work + finalize evaluation protocol & materials

Milestone: ready-to-run study protocol + consent + questionnaire

W11–14: Main user study (~10 participants)

Milestone: data collection completed (logs + ground truth counts + questionnaires)

W15–17: Analysis (accuracy + user feedback)

Milestone: results tables/plots + key findings drafted

W18–20: Thesis writing + final revisions + presentation material

Milestone: final report + slides ready for submission/presentation

USE OF GENERATIVE AI

Describe the way you used generative AI for writing your individual plan.

- Structure the individual plan according to the provided template and ensure all required sections were included.

- Improve clarity and academic tone in English (rewriting and proofreading).

- Help formulate and refine research questions, objectives, tasks, and evaluation criteria to be explicit and measurable.

- Produce concise draft text for sections such as ethics, sustainability, limitations, risks, and schedule based on the project description.

REFERENCES

List references, including information Authors, Title, Journal/Book/Conference/Website, Publication date